# InterviewBuddy

# Project Plan

# Version 1.2 Draft

# Revision History

| Date | Version | Description | Author |
| --- | --- | --- | --- |
| 16/Oct/26 | 1.0 | Initial draft of Sections 1, 2, and 3 (Introduction, Project Overview, Project Organization). | Lam Gia Hung |
| 17/Oct/26 | 1.1 | Complete Section 4 (Management Process, Schedule, Requirements & Risk Management). | Nguyen Dang Hoang Khang |
| 30/Oct/26 | 1.2 Draft | Added PA2 project-management content: feature estimates, schedule updates, reporting, configuration management and schedule risks. Earlier content retained; team review pending. | Lam Gia Hung |

# Table of Contents

1.	Introduction	4

1.1	Purpose	4

1.2	Scope	4

1.3	Overview	4

2.	Project Overview	4

2.1	Project Purpose, Scope, and Objectives	4

2.2	Assumptions and Constraints	6

2.3	Project Deliverables	7

3.	Project Organization	8

3.1	Organizational Structure	8

3.2	Roles and Responsibilities	8

4.	Management Process	9

4.1	Project Estimates	9

4.2	Project Plan	10

4.2.1	Phase Plan	10

4.2.2	Iteration Objectives	11

4.2.3	Releases	11

4.2.4	Project Schedule	11

4.2.5	Project Resourcing	13

4.3	Project Monitoring and Control	14

4.3.1	Requirements Management	14

4.3.2	Reporting and Measurement	14

4.3.3	Risk Management	15

4.3.4	Configuration Management	16

# Project Plan

# Introduction

## Purpose

This Software Development Plan defines how the InterviewBuddy project will be organized, developed, and monitored. It establishes a shared understanding of the project objectives, expected deliverables, team responsibilities, and planning approach.

The project team will use this document to coordinate work, identify dependencies between activities, and monitor progress against the agreed schedule. The project supervisor will use it to review the team’s direction and provide feedback. The plan will be updated as requirements, task assignments, and iteration objectives become clearer.

## Scope

This plan applies to the development of InterviewBuddy, a web application that provides AI-assisted mock interviews for job and internship seekers. It covers requirements analysis, interface design, implementation, testing, and delivery of the proposed application, together with the documentation and coordination activities needed to manage that work.

The plan addresses the project as a whole. Detailed iteration objectives, task owners, target dates, and build schedules will be maintained in Section 4.2 and the team’s Jira project. Changes to product scope or project priorities should be reflected consistently in this plan, the Vision Document, and the project schedule.

## Overview

Section 2 presents the project purpose, target users, proposed product scope, assumptions, constraints, and deliverables. Section 3 describes the team structure, supervision, and responsibilities for the project’s work areas. Section 4 describes project estimates, development phases and iterations, scheduling, resource allocation, and project monitoring and control.

# Project Overview

## Project Purpose, Scope, and Objectives

InterviewBuddy is a web application that helps users prepare for a particular job or internship interview. Users provide a job description and their CV so that the application can generate practice questions relevant to the position and the candidate’s background. During a mock interview, the AI interviewer asks one question at a time and uses the candidate’s answers to decide whether to ask a follow-up question, move to another topic, or finish the session.

The primary target users are third- and fourth-year students and recent graduates in Vietnam preparing for internships or their first jobs. Secondary users include career changers and early-career professionals preparing to switch jobs. The proposal also identifies people preparing for club or organization interviews as potential users.

The project has the following objectives:

| Objective | Description |
| --- | --- |
| Provide position-specific practice. | Use the job description and CV to identify relevant skills, experience, matches, and gaps, then use that context when generating interview questions. |
| Support interactive rehearsal. | Allow candidates to choose an interview round, difficulty level, and language, then answer questions and follow-up questions in a continuous session. |
| Provide actionable feedback. | Explain strengths and weaknesses in individual answers, refer to evidence from those answers, and provide a suggested answer or outline. |
| Support repeated improvement. | Generate practice questions based on weaker criteria and allow users to review previous sessions and changes in their scores. |

PA0 collected 15 responses through an online form. CV/JD analysis was rated as needed by 15/15 respondents, and interview chat with follow-up questions by 14/15. Detailed feedback supported by evidence from the answer was selected by 14/15 respondents. These results support the proposed focus on personalized questions and specific feedback. Because 13/15 respondents were students, the findings mainly describe student preferences.

The proposed product scope is described below.

| Feature area | Planned capabilities |
| --- | --- |
| Account and profile | Allow users to register or log in through email or Google and maintain information such as field of study, target position, and experience level. |
| JD and CV analysis | Accept a pasted job description and an uploaded PDF or pasted CV. Extract relevant skills and show matches and gaps between the CV and the position. |
| Interview configuration | Allow users to select HR, technical, or behavioral interviews, choose a difficulty level, and use Vietnamese or English. |
| Interactive interview | Present one question at a time and generate follow-up questions based on the candidate’s previous answer. |
| Answer input | Keep typed answers available. Support optional voice answers through transcription, with an opportunity to edit the transcript before submitting it. AI responses remain in text. |
| Answer feedback | Evaluate answers against the proposed rubric of content, STAR structure, clarity, and confidence; provide an explanation and a suggested answer or outline. The applicability and evidence for each criterion will be clarified during requirements elaboration. |
| Results and further practice | Present an overall score, scores by criterion, strengths, areas for improvement, and new questions targeting weaker criteria. |
| History and progress | Store previous sessions, show score trends, and allow users to bookmark useful questions. |
| Practice planner | Use the real interview date and current weaknesses to propose a daily practice schedule, then adjust it when sessions are missed or scores change. |
| Export and sharing | Allow users to export a report as PDF or create a read-only report link. |

Development priorities follow the direction proposed in PA0. CV/JD input, interview configuration, and chat with follow-up questions receive the earliest attention. Detailed feedback, reports, and targeted practice questions support the next part of the core workflow. History and progress tracking are prioritized before the daily practice planner. PDF export and report sharing are proposed after the main interview and feedback flow.

## Assumptions and Constraints

The plan is based on the following assumptions and constraints.

| Area | Assumption or constraint |
| --- | --- |
| Platform | InterviewBuddy will be delivered as a website accessible through desktop and mobile browsers. PA0 identifies Windows, macOS, Linux, Android, and iOS as user environments. |
| Connectivity | Users need an internet connection to access the application and complete the interview workflow. |
| Language | Mock interviews and practice content are planned for Vietnamese and English. The selected interview language should remain consistent throughout the session. |
| Voice input | Voice answers require a microphone and suitable browser support. Chrome and Edge are recommended in PA0; Safari and Firefox users must retain access to typed answers. |
| Transcript confirmation | Users must be able to review and edit a voice transcript before submitting it as their answer. The submitted text becomes the answer used by the interview and feedback functions. |
| AI reliability | AI-generated questions, scores, and suggestions may be inaccurate. Feedback should explain its basis, communicate uncertainty where appropriate, and present scores as practice guidance. |
| Speaking measurements | Filler words and answer length can be derived from a transcript. Speaking pace also requires answer-duration data. Vocal confidence cannot be assessed reliably from typed answers or transcripts alone. |
| Personal data | CVs, interview answers, and practice history may contain personal information. The application should explain how these data are used and allow users to delete their data. Permission must be requested before storing audio. |
| Report sharing | Sharing must be initiated by the user. A report intended for private practice should not become publicly accessible by default. |
| Team resources | The project is carried out by the five student members listed in PA0. Work assignments must account for the available team rather than assume additional staff. |
| Business scope | PA0 proposes a free first version. A paid plan and final price are to be considered after evaluating whether users return and find the feedback useful. |
| Schedule and budget | The five-sprint calendar and build targets are specified in Section 4.2. API spending and infrastructure limits will be agreed before paid resources are used. |

The proposed feature list may be refined during requirements analysis. When priorities change, the team should update the affected deliverables, dependencies, and schedule together so that the Vision Document and Software Development Plan remain consistent.

## Project Deliverables

The project will produce the following deliverables. Target milestones follow the phase and build schedule in Section 4.2.

| Deliverable | Expected contents | Target milestone |
| --- | --- | --- |
| Vision Document | Product problem, target users, proposed features, scope, priorities, and non-functional requirements. | Initial PA1 version by 18 Oct 2026; updated at later review milestones. |
| Software Development Plan | Project overview, organization, responsibilities, phase and iteration plan, schedule, and monitoring approach. | Initial PA1 version by 18 Oct 2026; revised after review and planning changes. |
| UI sketches | Three to six main screens illustrating the intended user flow, such as CV/JD input, interview setup, the interview session, and the results report. | PA1 submission by 18 Oct 2026. |
| Core InterviewBuddy application | The CV/JD analysis, interview configuration, question-and-answer flow, follow-up questions, answer feedback, reports, and targeted practice questions selected for the initial scope. | Build 1 on 15 Nov 2026 for the text interview flow; Build 2 on 29 Nov 2026 for feedback and reports. |
| History and progress functions | A list of past sessions, score trends, and bookmarks for useful questions. | Build 3 on 13 Dec 2026, following the core workflow. |
| Optional voice support | Microphone input, speech transcription, transcript editing before submission, and typed-answer fallback. | Build 2 on 29 Nov 2026; retain typed-answer fallback. |
| Later product features | The daily practice planner and PDF export or read-only report sharing, subject to the agreed scope and available effort. | Planner and PDF export targeted for Build 3 on 13 Dec 2026; read-only sharing subject to agreed scope. |
| Source code and verification records | Versioned application code, relevant setup instructions, verification results, and records of defects and their resolution. | Maintained throughout development and associated with each build. |
| Weekly progress reports | Completed work, remaining work, issues, and next actions for the two weeks in Inception, Sprint 1. | Two reports for Sprint 1, covering 5-11 Oct and 12-18 Oct 2026. |
| Weekly progress reports — Sprint 2 and PA2 | Done, Todo, Issues, next actions and Jira/Git/test evidence from each member; Nguyên compiles W4 and the Sprint 2 retrospective. | Internal PA2 review: 30 Oct 2026. Weekly Report W4, retrospective and PA2 submission: by 1 Nov 2026. Records are maintained in /docs/management. |

The initial application should support a complete practice flow: a user provides a CV and job description, configures an interview, answers questions, receives feedback, and reviews the resulting report. Completion of individual features should be assessed against this flow and their agreed acceptance criteria.

# Project Organization

## Organizational Structure

InterviewBuddy is developed by a five-member student team under the supervision of Mr. Truong Phuoc Loc. Đào Ngọc Chung Nguyên serves as the group leader and coordinates the team’s work.

| Student ID | Full name | Role identified in PA0 |
| --- | --- | --- |
| 24127466 | Đào Ngọc Chung Nguyên | Group Leader |
| 24127119 | Trần Phước Tài | Team Member |
| 24127410 | Nguyễn Đặng Hoàng Khang | Team Member |
| 24127476 | Nguyễn Trần Trung Nhân | Team Member |
| 24127389 | Lâm Gia Hưng | Team Member |

The project supervisor provides academic guidance and feedback on the project’s direction and deliverables. The group leader coordinates planning, task allocation, progress reporting, and communication of issues requiring guidance.

The team uses Jira for task planning and progress tracking, GitHub for source code and version history, and Google Drive for shared project documents. These tools are listed in PA0 and provide a common place to maintain the team’s work and supporting records.

Team members may hold more than one work responsibility during an iteration. Specific task ownership will be recorded in Jira and the project schedule, allowing responsibilities to change as the project moves from requirements and design to implementation and testing.

## Roles and Responsibilities

The following responsibilities define the work needed to deliver InterviewBuddy. Individual assignments for the functional work areas will be recorded in the iteration plans and Jira tasks.

| Role | Responsibilities |
| --- | --- |
| Project Supervisor — Mr. Truong Phuoc Loc | The project supervisor provides academic guidance, reviews the project’s direction, and gives feedback on the team’s deliverables. Questions affecting course expectations, project feasibility, or major scope decisions should be raised for guidance when needed. |
| Group Leader — Đào Ngọc Chung Nguyên | The group leader coordinates the team’s planning and delivery activities. Responsibilities include maintaining a shared understanding of priorities, ensuring that scheduled tasks have owners, checking progress and unresolved blockers, consolidating status reports, and checking consistency between the Vision Document, project plan, and schedule. The group leader also coordinates reviews of deliverables before submission and ensures that decisions affecting scope or deadlines are communicated to the team. |
| Project Team Members | All members are responsible for completing their assigned work, updating its status, reporting blockers, and providing the information needed for progress reports. Members should review work related to their own tasks and coordinate with others when one task depends on another. |

The functional responsibilities are as follows:

| Work area | Responsibilities | Expected outputs |
| --- | --- | --- |
| Requirements analysis | Convert PA0 findings into clear product requirements; define user flows and acceptance criteria; maintain feature priorities; clarify language support, browser behavior, privacy controls, and the evidence available for scoring. | Vision Document, prioritized requirements, user stories, and acceptance criteria. |
| UI and interaction design | Design the CV/JD input, interview setup, interview session, and report screens; show how users move between them; define typed-answer, voice-transcript confirmation, and relevant error or empty states. | UI sketches and agreed interaction flows. |
| Application development | Implement assigned features from the agreed scope; connect the input, interview, feedback, report, and history functions; maintain source code in GitHub and provide setup information needed by other members. | Working features, versioned source code, and setup instructions. |
| Quality assurance | Check the main practice flow and agreed acceptance criteria; verify that interview settings affect the session, edited transcripts are submitted correctly, and reports correspond to the recorded answers and scores; record and recheck defects. | Verification cases and results, defect records, and confirmed fixes. |
| Documentation and configuration | Maintain current project documents and links; identify document versions; record decisions affecting scope and delivery; keep progress reports consistent with Jira and the completed work. | Updated documents, decision records, and progress reports. |

Each scheduled task should identify one accountable owner, the expected output, the planned completion point, and the condition for considering it complete. Tasks involving several members should make their contributions and dependencies clear. This provides a concrete basis for tracking progress and reporting each member’s work.

# Management Process

## Project Estimates

We estimate the development effort for InterviewBuddy using the eleven features in our PA0 proposal. The total feature baseline is 71 story points (SP). These estimates support our sprint allocation and remain provisional because our Jira board does not yet contain story-point estimates or measured velocity. The baseline in this revision is dated 29 October 2026.

We use the relative scale 1, 2, 3, 5, 8 and 13 to compare complexity, effort and uncertainty. Each feature estimate covers design, implementation and feature-level verification. We allocate separate capacity for integration, regression testing and project documents. Story points have no fixed conversion to working hours.

| ID | Feature | SP | Estimation basis |
| --- | --- | --- | --- |
| F1 | Sign-up, login and profile | 5 | Authentication flows, profile fields and persistence. |
| F2 | JD/CV input and fit analysis | 8 | PDF/text input, skill extraction, comparison, result and error handling. |
| F3 | Mock interview setup | 3 | Round, difficulty and language selection with validation. |
| F4 | Text interview and follow-ups | 13 | Session state, contextual questions and follow-up/new-topic/end decisions. |
| F5 | Voice answers | 8 | Browser transcription, editable transcript and typed-answer fallback. |
| F6 | Per-answer scoring and feedback | 8 | Rubric, specific feedback and sample outline; split 3 SP in S3 and 5 SP in S4. |
| F7 | Post-interview report | 5 | Aggregated scores, strengths, gaps and supported speaking measures. |
| F8 | Targeted practice questions | 5 | Generate new questions from weaker report criteria. |
| F9 | History and progress | 5 | Session list, score trends and bookmarked questions. |
| F10 | Practice-plan agent | 8 | Daily schedule based on interview date and replanning after missed work. |
| F11 | PDF report export | 3 | Export a readable report; read-only link is subject to later scope agreement. |
|  | Total estimated feature work | 71 | Total feature baseline for Sprints 2–5; not remaining work. |

Our planning assumption is 25 SP per two-week sprint for a team of five, equivalent to an average allocation of 5 SP per member. This capacity has not yet been validated against individual availability or completed sprint work. F1 and F2 account for 13 SP in the full baseline; their parent tasks are marked Done in Sprint 2, although some subtasks remain open. We therefore use the remaining 58 feature SP to plan Sprints 3–5. Their combined capacity assumption is 75 SP, including a reserve of 17 SP for integration, regression testing, defects and documentation.

| Sprint | Feature SP | Capacity SP | Reserve SP | Planned feature allocation |
| --- | --- | --- | --- | --- |
| S3 | 19 | 25 | 6 | F3 3 + F4 13 + F6 design 3 |
| S4 | 23 | 25 | 2 | F5 8 + F6 completion 5 + F7 5 + F8 5 |
| S5 | 16 | 25 | 9 | F9 5 + F10 8 + F11 3 |
| Total S3–S5 | 58 | 75 | 17 | Integration, regression, defects and documentation. |

Sprint 4 carries the heaviest planned load at 23 of 25 SP, leaving a reserve of 2 SP. Our delivery priority is the integrated voice, feedback and report workflow. If this work exceeds capacity, we will review the allocation of F8 at the sprint review and record any schedule change in Jira. For F11, this estimate covers PDF export as the initial delivery option in PA0; a read-only sharing link remains outside the current estimate.

## Project Plan

PA2 planning supplement

Our PA2 work consolidates the requirements and initial design of InterviewBuddy: the updated plan, Vision, use cases, supplementary requirements, architecture and UI designs. The additions below record our Sprint 2 deliverables and the planned handoffs to later implementation and testing work. The five-sprint calendar and release milestones provide continuity with the earlier project plan.

We organize the project into five two-week sprints. The dates below follow our Jira backlog as of 29 October 2026. Sprint 2 focuses on the PA2 package and the foundations for the interview workflow. Our planned allocations for Sprints 3–5 connect each feature group to a demonstrable build; the corresponding Jira work items have not yet been assigned.

### Phase Plan

The InterviewBuddy project will follow an iterative process based on RUP and Scrum, organized into 3 main phases and 5 Sprints (2 weeks per Sprint):

Inception Phase (Sprint 1: Oct 5 - Oct 18): Focus on project proposal, user interviews (completed with 15 respondents), requirements gathering, and initial tools setup (GitHub, Jira).

Elaboration Phase (Sprint 2 & Sprint 3: Oct 19 - Nov 15): Focus on UI/UX design, AI integration architecture, system design, and delivering the first executable build featuring core text-based interview flow.

Construction Phase (Sprint 4 & Sprint 5: Nov 16 - Dec 13): Focus on integrating advanced features (Voice-to-text, AI scoring rubric, Practice-plan agent), comprehensive testing, and finalizing the product.

PA2 update to phase planning

| Phase | Sprint and dates | Objective and exit point |
| --- | --- | --- |
| Inception | S1, 5–18 Oct | PA0/PA1 proposal, research, initial plan, vision, UI sketches and project tools. |
| Elaboration | S2–S3, 19 Oct–15 Nov | Requirements and design; login, CV/JD analysis and first text interview build by 15 Nov. |
| Construction | S4–S5, 16 Nov–13 Dec | Voice, full feedback, report and practice features; then history, planner, PDF and final checks. |

### Iteration Objectives

Based on user research, the core personalized practice features will be developed first. The project will produce the following main builds:

Build 1 (End of Sprint 3 - Nov 15): Initial working software focusing on Features 1-4 (Login, CV/JD input, Interview settings, and Text-based chat with AI follow-up questions).

Build 2 (End of Sprint 4 - Nov 29): Integrated build adding Features 5-8 (Voice answers and transcription, Per-answer scoring with rubric, Post-interview reports, and Targeted practice questions).

Build 3 / Final Release (End of Sprint 5 - Dec 13): Final polished product including Feature 9-11 (History tracking, Practice-plan agent, PDF export) with full bug fixes and UI/UX optimization.

PA2 and subsequent sprint objectives

| Sprint | Feature work and coordination | Planned deliverable |
| --- | --- | --- |
| S1 | Project proposal, user research, vision, UI sketches, setup and weekly reports. | PA0 and PA1 artifacts; repository and Jira board. |
| S2 | F1–F2; PA2 requirements/design, Session API, UI setup, Project Plan v1.2 and AI interviewer spike. | PA2 package by 1 Nov: 17 use cases, Vision v1.2, Supplementary Specification, SAD/ERD, UI designs and Weekly Report W4. The sprint also covers the Session API, Setup/Profile pages, fit-analysis improvements and interviewer AI design. |
| S3 | F3–F4 and 3 SP of F6 rubric design; integrate the first text interview path. | Build 1: set interview options, receive questions and follow-ups, submit typed answers. |
| S4 | F5, remaining 5 SP of F6, F7 and F8; integrate voice, feedback and reporting. | Build 2: confirm a transcript, receive per-answer feedback, view a report and new practice questions. |
| S5 | F9–F11; integration, regression, bug fixes and delivery documents. | Build 3: history, planner and PDF export with a checked end-to-end workflow. |

### Releases

The project plans three main releases for demonstration and evaluation:

Release 1.0 (Alpha / Demo 1 - Nov 15, 2026 - End of Sprint 3): Internal demo release focusing on the core text-based interview flow, CV/JD input analysis, and basic user settings.

Release 2.0 (Beta / Demo 2 - Nov 29, 2026 - End of Sprint 4): Beta release incorporating Voice-to-text integration, rubric scoring engine, post-interview analytics report, and weakness-focused practice questions for initial user testing.

Release 3.0 (Final Release - Dec 13, 2026 - End of Sprint 5): The final production-ready release including the daily practice-plan agent, progress tracking, PDF export, and full bug fixes.

Acceptance focus for the planned releases

| Release | Target | Acceptance focus |
| --- | --- | --- |
| Release 1.0 / Alpha | 15 Nov 2026, end S3 | A candidate can enter CV/JD, configure and complete a typed AI interview; follow-up behavior is reviewable. |
| Release 2.0 / Beta | 29 Nov 2026, end S4 | Optional voice transcript is editable before submission; feedback, report and targeted questions work together. |
| Release 3.0 / Final | 13 Dec 2026, end S5 | History, progress, practice plan and PDF report complete the flow; priority defects are resolved. |

### Project Schedule

Figure 1: Sprint 1 task board and team assignments on Jira.

The project tasks, Sprints, and progress are managed and tracked using Jira (Board: Interview Buddy). Tasks are assigned to specific team members according to their roles:

Completed Tasks (Sprint 1 - Inception):

Set up Jira & Slack, submit Project Proposal (PA0) — Assigned to Đào Ngọc Chung Nguyên

Set up GitHub Repository and directory structure — Assigned to Nguyễn Trần Trung Nhân

Define and describe 11 Key Features — Assigned to Trần Phước Tài

Conduct user survey and write User Interviews report — Assigned to Trần Phước Tài

Conduct user survey and write User Interviews report — Assigned to Lâm Gia Hưng

Define Target Users and Environments — Assigned to Nguyễn Đặng Hoàng Khang

In Progress / In Review Tasks (PA1):

Draft Vision Document — Assigned to Nguyễn Trần Trung Nhân

Design UI Prototyping — Assigned to Trần Phước Tài

Draft Project Plan (Parts 1, 2, and 3) — Assigned to Lâm Gia Hưng

Draft Project Plan (Part 4 - Schedule & Management) — Assigned to Nguyễn Đặng Hoàng Khang

Compile Weekly Reports, Project Execution and Tracking — Assigned to Đào Ngọc Chung Nguyên

PA2 schedule and Jira snapshot

Our Sprint 2 planning snapshot on 29 October 2026 contains ten parent work items. Five are marked Done: project kickoff, deployment and reporting; application and database setup; the app shell and login page; the CV/JD input page; and the AI fit-analysis API. Five are In Progress: the PA2 package and Weekly Report W4; architecture, ERD and the Session API; Figma and the Setup/Profile pages; Vision, non-functional requirements and fit-analysis improvements; and the Project Plan and interviewer AI design. These parent statuses do not establish acceptance of every subtask. Sprint 2 has no recorded story points, while Sprints 3–5 have no assigned work items or recorded estimates. Sections 4.1 and 4.2 contain our proposed allocation for those future sprints.

| Sprint | Jira dates | Milestone | Dependencies and planned work |
| --- | --- | --- | --- |
| S1 | 5–18 Oct | PA0/PA1 baseline | PA0 and PA1 provide the planning inputs for later sprints. |
| S2 | 19 Oct–1 Nov | PA2 package; F1–F2 | We review PA2 internally on 30 Oct and target Moodle submission on 1 Nov; Sprint 3 planning follows the review. |
| S3 | 2–15 Nov | Build 1; F3–F4, F6 design | We build the first interview flow on the architecture and Session API prepared in Sprint 2. |
| S4 | 16–29 Nov | Build 2; F5–F8 | We integrate voice, scoring and reporting within a proposed 23 SP feature allocation. |
| S5 | 30 Nov–13 Dec | Build 3; F9–F11 | We verify the complete workflow, resolve priority defects and prepare the release records. |

### Project Resourcing

The project is developed by a five-member student team from FIT-VNUHCM:

Đào Ngọc Chung Nguyên (Group Leader): Coordinates planning, task allocation, progress reporting, and communication.

Trần Phước Tài, Nguyễn Đặng Hoàng Khang, Nguyễn Trần Trung Nhân, Lâm Gia Hưng (Project Team Members): Responsible for completing assigned work across various functional areas (Requirements analysis, UI/UX design, Application development, Quality assurance, Documentation).

As this is an academic project, team members will share cross-functional responsibilities and may hold more than one work responsibility during an iteration. Specific task ownership (e.g., frontend, backend, testing) will be dynamically allocated and recorded in Jira and the project schedule for each Sprint based on the current iteration's needs. All members will utilize the required tools (Jira, GitHub, Slack) to manage their work and collaborate effectively

PA2 work allocation

We divide the current work across five members. Chung Nguyên coordinates the project, requirements packaging and progress reporting. Trung Nhân handles architecture, database work and the Session API. Tài handles interface design, authentication and the Setup/Profile pages. Khang handles CV/JD input and the Vision and Supplementary Specification. Hưng handles the Gemini integration, AI design work and this Project Plan. Individual issue owners are recorded in Jira. Assignments for Sprints 3–5 are pending sprint planning.

## Project Monitoring and Control

### Requirements Management

The product requirements for InterviewBuddy are captured in the Vision document and Use Case models.

All requirement artifacts are stored in the /docs/requirements folder within the team's GitHub repository: https://github.com/TrungNhan8386/InterviewBuddy.

Changes to requirements or feature modifications will be managed as Issues on the Jira board.

The team utilizes a dedicated Slack channel to discuss, review, and approve any requirement changes before implementation.

### Reporting and Measurement

We use Jira to track the owner, scope, due date, status and acceptance criteria of each work item. Each member updates their issues when work starts, a blocker appears or evidence is ready for review. Nguyên consolidates these updates at the midweek sync and sprint review. We record unfinished work and its reason before moving it to a later sprint.

Our weekly report records Done, Todo, Issues and next actions, with links to Jira issues, commits or pull requests and test evidence. Each member supplies their own progress; Nguyên compiles the report in /docs/management. For Sprint 2, our internal PA2 review is scheduled for 30 October 2026. Weekly Report W4, Moodle submission and the Sprint 2 retrospective are scheduled by 1 November 2026.

| Measure | Record and interpretation | Review and response |
| --- | --- | --- |
| Work progress | Counts of To Do, In Progress and Done items, overdue items and blockers. Parent and subtask counts are reported separately. | Issue owners update on change; Nguyên reviews at the midweek sync and sprint end and records an owner and next action for each blocker. |
| Sprint effort | Committed, accepted and remaining SP. Completion rate = accepted SP / committed SP × 100 when committed SP is nonzero. Velocity is accepted SP per completed sprint. | We review at sprint end. Missing estimates are reported as unavailable. Section 4.1 contains planning estimates; these are not measured velocity. |
| Defects | New, open, fixed and retested defects, grouped by severity. Each Jira defect includes steps, expected/actual results, affected build and evidence. | The tester logs a defect; its owner fixes it and a reviewer records the retest. A failed retest returns the defect to active work. |
| Build readiness | Required check results, failed acceptance cases and unresolved defects linked to the build and pull request. | Before merge or release, Nhân reviews the evidence with the change owner. Blocking defects are fixed or the affected scope is deferred with a recorded decision. |

We keep actual measurements separate from estimates. At the 29 October planning snapshot, Jira had no recorded Sprint 2 story points; this document therefore does not claim a measured velocity or completion percentage. Defect counts are taken from a dated Jira review rather than inferred from missing records. At each retrospective, we record the problem, agreed action, owner and target date in our management records.

### Risk Management

Risks will be identified in Inception Phase using the steps identified in the RUP for Small Projects activity “Identify and Assess Risks”. Project risk is evaluated at least once per iteration and documented in this table. The risks of the greatest magnitude are listed first in the table.

| Risk level | Risk Description and Impact | Mitigation Strategy and/or Contingency Plan |
| --- | --- | --- |
| High | AI Hallucination & Generic Feedback: The AI might generate incorrect suggestions or generic feedback that does not strictly follow the CV/JD (a concern raised by respondent R06 and R13). | Carefully design and refine AI Prompts (Prompt Engineering) for the interviewer and scoring agent. Provide strict constraints and context limits for the AI model. |
| High | High latency in Voice & AI processing: Speech-to-text transcription and AI text generation may take too long, ruining the real-time interview experience. | Utilize streaming API responses (like ChatGPT/Gemini stream) to display text as it generates. Implement UI loading states to manage user expectations. |
| High | PA2 schedule and handoff risk: the plan, use cases, Vision, SAD and UI depend on cross-review and timely handoffs between document owners. A late input can delay the 30 October internal review or leave the 1 November submission incomplete. | We track handoff owners, due dates and blockers in Jira. Nguyên coordinates the final package; each owner resolves review comments. We prioritize required PA2 artifacts, record deferred scope and escalate a missed handoff at the next sync. |
| High | Sprint 4 integration load: voice input, scoring, reporting and targeted practice use 23 of the proposed 25 SP. A 2 SP reserve may be insufficient when API or integration defects occur. | We review integration dependencies before Sprint 4, verify interfaces early and monitor remaining work during the sprint. We prioritize the voice-feedback-report flow and review F8 allocation if capacity is exceeded; schedule changes are recorded in Jira. |
| Medium | API Cost Limit: Extensive testing of LLMs and Speech-to-text APIs could exceed the team's free-tier limits or budget. | Use cost-effective models (e.g., mini or flash models) during development. Mock AI responses for basic UI testing to save API calls. |
| Medium | Privacy concerns with CV data: Users (like respondent R08) might hesitate to upload CVs containing personal information. | Add a clear privacy disclaimer. Design the system to not permanently store uploaded CV PDFs, extracting only necessary skill data for the session. |

### Configuration Management

We maintain application code and project documents in the InterviewBuddy GitHub repository. Our change workflow uses a dedicated feature, fix or documentation branch linked to its Jira issue, for example docs/project-controls. Commits describe the change and reference the issue; related pull requests include the scope, affected files and verification evidence.

We submit changes through a pull request to main. A member other than the author reviews the change, and Nhân coordinates the merge after review comments and required checks are resolved. Code changes include relevant tests and a build check; document changes include content and layout checks. Before merging, we reconcile changes against the current main branch. If an integrated change causes a regression, we record the defect and restore the last accepted behavior through a reviewed revert or corrective pull request.

For the releases in Section 4.2, our planned tag names are v1.0.0-alpha, v2.0.0-beta and v3.0.0. We create a tag on the accepted main commit after its build is verified. Each release record identifies the commit, date, delivered scope, verification results and known limitations; these planned names do not indicate that a release has already been published.

| Repository location | Managed content | Responsibility |
| --- | --- | --- |
| /src | Application, API routes, configuration examples and database changes. | Nhân coordinates integration; each change has an issue owner. |
| /docs/management | Project plans, weekly reports and retrospective records. | Hưng maintains the plan; Nguyên consolidates reporting. |
| /docs/requirements | Vision, use cases, supplementary requirements and traceability. | Nguyên and Khang maintain their assigned artifacts. |
| /docs/analysis and design | Architecture, ERD, UI designs and AI design findings. | Nhân, Tài and Hưng maintain their assigned artifacts. |
| /docs/api | API contracts and request/response examples. | The API owner maintains the contract used by consumers. |
| /docs/test | Test evidence, anonymized samples and verification records. | The test author records results for the relevant issue and build. |
| /pa | Copies of submitted assignment packages. | Nguyên assembles and maintains submission copies. |

We preserve prior revision-history entries and add a new record when an artifact revision is finalized. The artifact owner edits its main content; reviewers record comments through the agreed review channel. Our PA2 baseline links the reviewed document versions to the corresponding repository commit. We keep API keys and test passwords in local or hosting environment variables; committed .env.example files contain placeholders. Shared CV/JD test samples are anonymized, and verification records identify the tested version without exposing credentials.